## Sheet1
Intelligent Planning and Modeling
Q1
Task 1a: Delivery of a tool set that allows planning and sensor processing systems to easily query and utilize the information stored in the world model. Formal draft of semantic world representation capable of supporting orders and plans for mixed-palletizing. | 1 | 9000 | 63000 | 72000
Task 1b:Establish relationship with IEEE RAS Glossary/Ontology working group and keep the group aware of our work in representations. | 1 | 9000 | 1000 | 10000
Task 2: A paper detailing the study and comparison of existing techniques will be created and submitted to a conference. | 1 | 24000 | 52000 | 76000
Task 3: A planning document will be created and circulated in the USARSim community that outlines an implementation strategy for developing the ability to include high-level semantic knowledge in the simulation. | 1 | 37000 | 2000 | 39000
Q2
Task 1a: Delivery of a tool set that allows planning and sensor processing systems to easily query and utilize the information stored in the world model. Formal draft of a representation for the semantic world representation that is capable of supporting orders and plans for mixed-palletizing. This draft will be presented to our working group consisting of industrial stakeholders and will contain knowledge of the orders, packages, robot, and final plans. | 1 | 5000 | 37000 | 42000
Task 1b: Brief IEEE RAS Glossary/Ontology working group on our tools. | 1 | 10500 |  | 10500
Task 1d: Industry workshop where representations developed in Task1Q1 will be presented. This will occur at the Modex show on 6-12 Feb in Atlanta, GA. | 1 | 5000 | 31000 | 36000
Task 2: A planning system based on leading edge techniques will be developed for creating mixed palletizing static plans. This system will use a simple world model representation. | 1 | 22500 | 2000 | 24500
Task 3: The semantic knowledge representation will be developed and embedded in an example environment. | 1 | 36000 | 2000 | 38000
Q3
Task 1a: Initial report on the knowledge needed for truck loading. This will include knowledge of the orders, pallets, robots, and limited information about the environment. Delivery of a tool set that allows planning and sensor processing systems to easily query and utilize the information stored in the world model. With reduced budget, this will go through Q4. | 1 | 9000 | 103000 | 112000
Task 1b: Brief IEEE RAS Glossary/Ontology working group on our work in truck loading and environmental representations | 1 | 9000 |  | 9000
Task 2: The planning system will be augmented to use the tools developed in task 1. | 1 | 22500 | 2000 | 24500
Task 3: An integrated system that allows virtual sensing of high-level semantic knowledge to be extracted from the simulation will be delivered. | 1 | 36000 | 3000 | 39000
Q4
Task 1a: Delivery of a modified tool set that allows planning systems to easily query and use the information stored in the combined world model. Delivery of a tool set that allows planning and sensor processing systems to easily query and utilize the information stored in the world model. With reduced budget, this will go through Q4. | 1 | 9000 | 42000 | 51000
Task 1b: Brief IEEE RAS Glossary/Ontology working group on our new tools and planning systems | 1 | 9000 |  | 9000
Task 2: A planning system capable of dynamic planning (changing the plan based on the world model) will be developed. | 1 | 22500 |  | 22500
Task 3: A method will be developed to allow the simulation system to communicate with the planner developed in task 2 to perform pallet stacking operations. An integrated system that allows virtual sensing of high-level semantic knowledge to be extracted from the simulation will be delivered. | 1 | 36000 | 3000 | 39000
Total for Intelligent Planning and Modeling |  | 311000 | 343000 | 654000