## Tasks
Tom |  |  |  |  | Zeid |  |  |  |  | Anthony
Task | Priority | Status | Supported Milestone | Anticipated Completion Date | Task | Priority | Status | Supported Milestone | Anticipated Completion Date | Task | Priority | Status | Supported Milestone | Anticipated Completion Date
Putting plans in ontology | 1 |  | Q4-1 |  | Autogenerate PDDL Init, Goal and Problem Files from Ontology | 2 |  | Q1-3 |  | RCC8 -> Predicates Truth Values | 3 |  | Q3-2
Maintain KittingClasses.owl | low | maintenance mode | Q1-2, Q1-3, Q2-3, Q3-2 |  | Action Failures | low |  | Q4 (removed) |  | GUI to create predicates from RCC8 relations | 4 |  | Q3-2
Maintain KittingInstances.owl | low | maintenance mode | Q1-2, Q1-3, Q2-3, Q3-2 |  | Flexibility Milestone | 3 |  | Q4-2 | 2013-03-31 | OWL2XML converter (converts OWL instances to XML instances to generate the init file for the kitting viewer) | 2 |  | Q3-1
Maintain kitting.xsd | low | maintenance mode | Q1-2, Q1-3, Q2-3, Q3-2 |  | Tool tip problem USARSim/ROS | 1 |  | Q2-2 (and others) | 2013-03-31 | Fix the scene generator | 1 |  | Q2-2 (and others)
Maintain xml2owl converter (converts xml kititng instances to owl kitting instances) | low | maintenance mode | Q1-2, Q1-3, Q2-3, Q3-2 |  | CASE paper | 1 |  | Q3-1 | 2013-03-05 | Paper focusing on linking the ontology to the mysql database and the c++ classes to access the MySQL database | 5 |  | ???
Maintain KittingInstances.xml | low | maintenance mode | Q1-2, Q1-3, Q2-3, Q3-2
Build a general purpose system that will generate KittingClasses.owl from KittingClasses.xsd (not kitting specific) | 5 |  | Q1-2, Q1-3, Q2-3, Q3-2
Maintain Kitting Viewer tool | 2 | initial version complete but needs to be improved | Q3-1
Update NISTIR / Kitting Viewer Users Manual | 3 |  | Q3-1
CASE paper | 4 |  | Q3-1 | 2013-03-07

## Milestones
FY 2013 Milestones:
Q1
1. Output - Present a white paper that will be shared with our MODEX workshop attendees and the IEEE working group that begins a discussion on flexibility and agility. What does it mean to be flexible? What does it mean to be adaptable? What aspects of the system require flexibility/adaptability to yield the largest payoffs? (Balakirsky & Kootbally)
2. Augment the data abstraction to include anticipated failure modes of actions and the probabilities associated with them for the kitting application. (Kramer & Kootbally)
3. Automatically populate the Planning Language of our architecture from the Ontology. (Schlenoff & Kootbally)
4. Output - Submit a paper detailing our state-based approach to ontology updating. (Schlenoff)
Q2
1. Develop metrics to determine how flexible and agile a kitting system is. These will be based on the definitions from Q1. (Kramer)
2. Develop test methods that provide a means of testing a kitting system’s flexibility and agility using the definitions produced in Q1 and the metrics produced in Q2. (Balakirsky & Kramer)
3. Populate specific instances of failure modes for the kitting domain into the ontology and deliver the updated ontology to the IEEE working group. (Kootbally)
4. Output - Previously developed an interface language for communicating between a high-level planning system and a lower-level planning system. This interface language will be delivered as a report to the IEEE working group for use in the standards activities. (Balakirsky)
Q3
1. Develop a visualization/data tool that will allow users to visualize the execution of kitting plans formulated in the interface language and gather statistics on those plans for use in performance evaluation. (Kramer)
2. Develop a representation of detailed state information within the ontology and real-time knowledge base for the kitting application. (Schlenoff)
Q4
1. Augment the ontology to support the representation of plans. (Kramer)
2. Output - Present a report to the IEEE Working Group detailing our definitions of flexibility, the test methods that may be used to demonstrate flexibility, and describe how a knowledge representation can aid in assuring system flexibility and agility. (Schlenoff & Kootbally)